September
week4	1.- deliber chapter 4 for review 2.- pre-review: enhancing chapter5.Conclusions 3.- pre-review: extending MDP and UCT description 4.- working chapter1, chapter2 for deliber
week5>	1.- deliber chapter5 “Conclusions” for review 2.- deliber chapter1 for review 3.- deliber chapter2 for review / 4.- receiving chapter 4 corrections(?) 5.- working on chapter 3 : Gujarat description, Agent model for Gujarat, technical aspects of AI 6.- working chapter 4 corrections	draft paper for model 0
October
<week1	September.week5, October.week1, are the same
week2	1.- deliber chapter 3 for review / 2.- receiving chapter 5 corrections(?) 3.- working chapter 4 corrections 4.- working chapter 5 corrections
week3	1.- deliber chapter 4 for review 2 2.- deliber chapter 5 for review 2 / 3.- receiving chapter 1 corrections(?) / 4.- receiving chapter 2 corrections(?) / 5.- receiving chapter 3 corrections(?) / 6.- work chapter 3 corrections
week4	1.- deliber chapter 3 for review 2 / 2.- receiving chapter 4 corrections(?) / 3.- receiving chapter 5 corrections(?) 2.- working chapter 1 corrections / 3.- working chapter 2 corrections
week5	1.- deliber chapter 1 for review 2 / 2.- deliber chapter 2 for review 2 3.- receiving chapter 3 corrections(?) 4.- working chapter 3 corrections / 5.- working chapter 4 corrections / 6.- working chapter 5 corrections
November	CLOSING CORRECTIONS
week1	October.week5, November.week1 are the same
week2
week3
week4
week5
December
week1	Document is perfect
week2
week3
week4
week5